## Sheet1
[7 empty] | Team Members | [10 empty] | Instructions: Fill in only green portions. For the activities table put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Readjust cell size to be sure all text is visible as needed.
[7 empty] | First Name | Last Name | Nickname (max 6 characters)
[7 empty] | Sai Teja | Pamulapati | Sai
[7 empty] | Srikanth | Vadlamudi | SV
[7 empty] | Kavya | Murugan | Kavya
[7 empty] | Pradheep | Shankar | PS
[7 empty] | Het Bimalkumar | Shah | Het
[7 empty] | Abhinaw Siddharth | Bogadhi | AS
Add more rows as necessary
Activities Table
Date | Who | [5 empty] | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| Sai | SV | Kavya | PS | Het | AS |  |  |  |  | Sai | SV | Kavya | PS | Het | AS
Milestone 1
2024-01-30 | 1 | 1 | 1 | 1 | 1 | 1 | Brainstorming session | 2 | Discuss possible ideas. | Everyone should come up with one system and present it to the team. | 2 | 2 | 2 | 2 | 2 | 2
2024-01-31 |  |  | 1 |  |  |  |  | 3 | Domain analysis. | Worked on analysing car rental application system for project proposal by listing features, requirements. Exploring java and papyrus | 0 | 0 | 3 | 0 | 0 | 0
2024-02-01 |  |  |  | 1 |  |  |  | 2 | Domain analysis. | Preparing for individual proposal for "travel booking management system" and proposing domain analysis | 0 | 0 | 0 | 2 | 0 | 0
2024-02-01 |  | 1 | [5 empty] | 3 | Domain analysis. | worked on smart home control system model and exploring papyrus | 0 | 3 | 0 | 0 | 0 | 0
2024-02-02 |  |  |  |  | 1 |  |  | 2 | Domain analysis. | Worked on Idea of E-commerce order processing system. To be precise researched on Domain analysis, listing out features, possible classes for the system, brainstormed possible OCL constraints, interesting cases which can be undertaken for sequence diagram and classes for state diagram. Prepared presentation to organize the possible idea for presenting it to group members. | 0 | 0 | 0 | 0 | 2 | 0
2024-02-02 | [5 empty] | 1 |  | 3 | Domain analysis. | Worked on " Car Parking Management System" proposal and exploring VS Code, Papyrus and Eclipse. | 0 | 0 | 0 | 0 | 0 | 3
2024-02-03 | 1 | [6 empty] | 2 | Domain analysis. | Worked on Library Management System. Designed a sample Class Diagram | 2 | 0 | 0 | 0 | 0 | 0
2024-02-04 | 1 | 1 | 1 | 1 | 1 | 1 | Brainstorming session | 3 | Finalize on the system. Distribution of tasks for milestone 1. | We considered everyones proposals and decided to do Library Management System. | 3 | 3 | 3 | 3 | 3 | 3
2024-02-08 |  | 1 | 1 |  |  |  |  | 1.5 |  | Completion of textual description of the system, including the objective of the system, potential users or customers, and a detailed list of features. | 0 | 1.5 | 1.5 | 0 | 0 | 0
2024-02-09 | [5 empty] | 1 |  | 2 | System requirements. | Non-fuctional use cases. | 0 | 0 | 0 | 0 | 0 | 2
2024-02-11 | 1 | 1 | 1 | 1 | 1 | 1 | Brainstorming session | 3 | Discuss the use case diagram | Discussed on the use case diagram | 3 | 3 | 3 | 3 | 3 | 3
2024-02-13 | 1 | 1 | 1 | 1 | 1 | 0 | Brainstorming session | 2 | Finalize the use case diagram | We finalized the use case diagram. We included all the possible use cases for a Library Management System | 2 | 2 | 2 | 2 | 2 | 0
2024-02-16 |  |  |  |  | 1 |  | UML use case | 1.5 | Papyrus Use case design | Initial design of use case diagram in Papyrus Software | 0 | 0 | 0 | 0 | 1.5 | 0
2024-02-18 |  |  |  |  | 1 |  | UML use case Correction | 1 | Minor correction and organizing use case diagram in Papyrus | Final Design of the use case diagram in Papyrus. | 0 | 0 | 0 | 0 | 1 | 0
2024-02-18 | 1 | 1 | 1 | 1 | 1 | 1 | Report Writing | 2 | Report creation | We discussed on the report format and completed the report | 2 | 2 | 2 | 2 | 2 | 2
2024-02-18 | 1 |  |  | 1 |  | 1 | Report Writing | 2 | Report Formatting | Report Editing | 2 | 0 | 0 | 2 | 0 | 2
[10 empty] | Total hours | 14 | 16.5 | 16.5 | 14 | 16.5 | 15
[10 empty] | Total team hours | [6 empty] | 92.5
Milestone 2
2024-02-19 | [5 empty] | 1 | Coding | 2.5 | User account login and creation. | Created user account login & creation .java files and pushed on github. | 0 | 0 | 0 | 0 | 0 | 2.5
2024-02-20 | [5 empty] | 1 | Coding | 3.5 | User repository | Created User repository and added user authentication feature. Updated UserLogin, UserRegistration, App.java files. | 0 | 0 | 0 | 0 | 0 | 3.5
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 0 | 0 | 0 | 0 | 0 | 6
[10 empty] | Total team hours | [6 empty] | 6
Milestone 3
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total team hours | [6 empty] | 0
Milestone 4
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total Team hours | [6 empty] | 0
Milestone 5
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | total team hours | [6 empty] | 0
[10 empty] | Total hour over project | 14 | 16.5 | 16.5 | 14 | 16.5 | 21
[10 empty] | Total team hours over project | [6 empty] | 98.5