## Sheet1
[7 empty] | Team Members | [10 empty] | Instructions: Fill in only green portions. For the activities table put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Readjust cell size to be sure all text is visible as needed.
[7 empty] | First Name | Last Name | Nickname (max 6 characters)
[7 empty] | Sai Teja | Pamulapati | Sai
[7 empty] | Srikanth | Vadlamudi | SV
[7 empty] | Kavya | Murugan | Kavya
[7 empty] | Pradheep | Shankar | PS
[7 empty] | Het Bimalkumar | Shah | Het
[7 empty] | Abhinaw Siddharth | Bogadhi | AS
Add more rows as necessary
Activities Table
Date | Who | [5 empty] | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| Sai | SV | Kavya | PS | Het | AS |  |  |  |  | Sai | SV | Kavya | PS | Het | AS
Milestone 1
2024-01-30 | 1 | 1 | 1 | 1 | 1 | 1 | Brainstorming session | 2 | Discuss possible ideas. | Everyone should come up with one system and present it to the team. | 2 | 2 | 2 | 2 | 2 | 2
2024-01-31 |  |  | 1 |  |  |  |  | 3 | Domain analysis. | Worked on analysing car rental application system for project proposal by listing features, requirements. Exploring java and papyrus | 0 | 0 | 3 | 0 | 0 | 0
2024-02-01 |  |  |  | 1 |  |  |  | 2 | Domain analysis. | Preparing for individual proposal for "travel booking management system" and proposing domain analysis | 0 | 0 | 0 | 2 | 0 | 0
2024-02-01 |  | 1 | [5 empty] | 3 | Domain analysis. | worked on smart home control system model and exploring papyrus | 0 | 3 | 0 | 0 | 0 | 0
2024-02-02 |  |  |  |  | 1 |  |  | 2 | Domain analysis. | Worked on Idea of E-commerce order processing system. To be precise researched on Domain analysis, listing out features, possible classes for the system, brainstormed possible OCL constraints, interesting cases which can be undertaken for sequence diagram and classes for state diagram. Prepared presentation to organize the possible idea for presenting it to group members. | 0 | 0 | 0 | 0 | 2 | 0
2024-02-02 | [5 empty] | 1 |  | 3 | Domain analysis. | Worked on " Car Parking Management System" proposal and exploring VS Code, Papyrus and Eclipse. | 0 | 0 | 0 | 0 | 0 | 3
2024-02-03 | 1 | [6 empty] | 2 | Domain analysis. | Worked on Library Management System. Designed a sample Class Diagram | 2 | 0 | 0 | 0 | 0 | 0
2024-02-04 | 1 | 1 | 1 | 1 | 1 | 1 | Brainstorming session | 3 | Finalize on the system. Distribution of tasks for milestone 1. | We considered everyones proposals and decided to do Library Management System. | 3 | 3 | 3 | 3 | 3 | 3
2024-02-08 |  | 1 | 1 |  |  |  |  | 1.5 |  | Completion of textual description of the system, including the objective of the system, potential users or customers, and a detailed list of features. | 0 | 1.5 | 1.5 | 0 | 0 | 0
2024-02-09 | [5 empty] | 1 |  | 2 | System requirements. | Non-fuctional use cases. | 0 | 0 | 0 | 0 | 0 | 2
2024-02-11 | 1 | 1 | 1 | 1 | 1 | 1 | Brainstorming session | 3 | Discuss the use case diagram | Discussed on the use case diagram | 3 | 3 | 3 | 3 | 3 | 3
2024-02-13 | 1 | 1 | 1 | 1 | 1 | 0 | Brainstorming session | 2 | Finalize the use case diagram | We finalized the use case diagram. We included all the possible use cases for a Library Management System | 2 | 2 | 2 | 2 | 2 | 0
2024-02-16 |  |  |  |  | 1 |  | UML use case | 1.5 | Papyrus Use case design | Initial design of use case diagram in Papyrus Software | 0 | 0 | 0 | 0 | 1.5 | 0
2024-02-18 |  |  |  |  | 1 |  | UML use case Correction | 1 | Minor correction and organizing use case diagram in Papyrus | Final Design of the use case diagram in Papyrus. | 0 | 0 | 0 | 0 | 1 | 0
2024-02-18 | 1 | 1 | 1 | 1 | 1 | 1 | Report Writing | 2 | Report creation | We discussed on the report format and completed the report | 2 | 2 | 2 | 2 | 2 | 2
2024-02-18 | 1 |  |  | 1 |  | 1 | Report Writing | 2 | Report Formatting | Report Editing | 2 | 0 | 0 | 2 | 0 | 2
[10 empty] | Total hours | 14 | 16.5 | 16.5 | 14 | 16.5 | 15
[10 empty] | Total team hours | [6 empty] | 92.5
Milestone 2
2024-02-19 | [5 empty] | 1 | Coding | 2.5 | User account login and creation. | Created user account login & creation .java files and pushed on github. | 0 | 0 | 0 | 0 | 0 | 2.5
2024-02-20 |  |  | 1 |  |  |  | UML class diagram | 3 | Worked on completing UML class diagram | Designed the classes in papyrus for the project for all assets | 0 | 0 | 3 | 0 | 0 | 0
2024-02-20 | [5 empty] | 1 | Coding | 3.5 | User repository | Created User repository and added user authentication feature. Updated UserLogin, UserRegistration, App.java files. | 0 | 0 | 0 | 0 | 0 | 3.5
2024-02-21 |  |  | 1 |  |  |  | UML class diagram | 3 | Worked on completing UML class diagram | Designed the classes in papyrus for the project for all users classes | 0 | 0 | 3 | 0 | 0 | 0
2024-02-21 | [5 empty] | 1 | Coding | 2 | Update User Authentication | Update user authentication, login and registration. | 0 | 0 | 0 | 0 | 0 | 2
2024-02-21 |  | 1 |  |  |  |  | Coding and review | 3 | Java setup, coding and review | Reviewing peers code and updating | 0 | 3 | 0 | 0 | 0 | 0
2024-02-22 |  |  |  | 1 |  |  | Coding | 3.5 | User login and register add and remove user | Functionality implementation | 0 | 0 | 0 | 3.5 | 0 | 0
2024-02-22 |  | 1 |  |  |  |  | Coding | 4.5 | Coding for classes | Classes creation and setup | 0 | 4.5 | 0 | 0 | 0 | 0
2024-02-22 | 1 | [5 empty] | Coding | 3.5 | Coding | Student Browse assets implemented along with advanced search | 3.5 | 0 | 0 | 0 | 0 | 0
2024-02-23 | 1 | [5 empty] | Coding | 3 | Coding | Browsing history Implemented | 3 | 0 | 0 | 0 | 0 | 0
2024-02-23 |  |  |  | 1 |  |  | Coding | 3 | Block and unBlock user update for admin | Functionality implementation for admin | 0 | 0 | 0 | 3 | 0 | 0
2024-02-24 |  |  |  | 1 |  |  | Coding | 1 | Update without togglecase | Rework on functional case without togglecase | 0 | 0 | 0 | 1 | 0 | 0
2024-02-24 | 1 | [5 empty] | Coding | 2 | Coding | Code Refactoring and correcting the attributes in the classes | 2 | 0 | 0 | 0 | 0 | 0
2024-02-24 |  |  |  |  | 1 |  | Reviewing | 3.5 | Understanding the code classes with respect to class Diagram and reviewing peer's code for asset management and asset repository. | Developed an idea of which functionalities of assetmanagement and assetrepository class is to be used for implementing add and remove for book and other assets. | 0 | 0 | 0 | 0 | 3.5 | 0
2024-02-25 | 1 | 1 | 1 | 1 | 1 | 1 | Group Discussion | 3 | Group Discussion | Discussion on Class Diagram and task break down | 3 | 3 | 3 | 3 | 3 | 3
2024-02-25 | [5 empty] | 1 | Coding | 1 | addUser message suppression | Suppresses addUser message for initial usecase. | 0 | 0 | 0 | 0 | 0 | 1
2024-02-25 |  |  |  |  | 1 |  | Coding | 4 | Coding for add and remove asset | Functionality developed for add and remove asset. | 0 | 0 | 0 | 0 | 4 | 0
2024-02-25 | 1 | [5 empty] | Review | 2 | Code Review | Reviewing peers code | 2 | 0 | 0 | 0 | 0 | 0
2024-02-25 |  |  |  |  | 1 |  | Coding | 3 | ReCoding for add and remove book as an individual asset rather then all asset in common because of different attributes. | Fully functional add and remove book code. | 0 | 0 | 0 | 0 | 3 | 0
2024-02-25 |  |  | 1 |  |  |  | Coding | 2 | Beginning the skeleton code for Non academic users in git | completed the raw template for Non academic user | 0 | 0 | 2 | 0 | 0 | 0
2024-02-26 |  |  |  |  | 1 |  | Refactoring and learning | 4 | Identified and reviewed mistakes as pointed out by peer. Learned new java concept of super and implmenting that in the add and remove book | Refactored Add and Remove Book code. | 0 | 0 | 0 | 0 | 4 | 0
2024-02-27 | 1 | 1 | 1 | 1 | 1 | 1 | Group Discussion | 2 | Group Discussion | Discussion on the tasks | 2 | 2 | 2 | 2 | 2 | 2
2024-02-27 |  |  | 1 |  |  |  | Coding | 3.5 | Adding the paid users options for all paid user functionalities | Completed and comitted it | 0 | 0 | 3.5 | 0 | 0 | 0
2024-02-27 | [5 empty] | 1 | Coding | 3 | Disciussion Room function | Added discussion room repository | 0 | 0 | 0 | 0 | 0 | 3
2024-02-28 |  |  |  | 1 |  |  | Coding | 4 | Test cases for User, blocking and userRepository | writing Junit testcases for the mentioned classes | 0 | 0 | 0 | 4 | 0 | 0
2024-02-28 |  | 1 |  |  |  |  | Coding | 5 | Coding for newsletter functionality for users classes | View news functionality | 0 | 5 | 0 | 0 | 0 | 0
2024-02-28 |  |  | 1 |  |  |  | Coding | 3 | coding for membership class, and repository for membership class | added association class for non academic user | 0 | 0 | 3 | 0 | 0 | 0
2024-02-28 | 1 | [5 empty] | Review | 1 | Code Review | Reviewing peers code | 1 | 0 | 0 | 0 | 0 | 0
2024-02-29 |  |  | 1 |  |  |  | Coding | 3 | Coding for free users and adjusting class member function in userlogin.java` | Completed the code for the free users | 0 | 0 | 3 | 0 | 0 | 0
2024-02-29 |  |  |  | 1 |  |  | Coding and debugging | 6 | Line edits, UI Changes, to string(), updateNews implementation | UI editing, implementation of toString() method and implementation of updateNews functionality | 0 | 0 | 0 | 6 | 0 | 0
2024-02-29 |  | 1 |  |  |  |  | Coding | 3.5 | Coding for test unit | View news test unit | 0 | 3.5 | 0 | 0 | 0 | 0
2024-02-29 | 1 | [5 empty] | Review | 1 | Code Review | Reviewing peers code | 1 | 0 | 0 | 0 | 0 | 0
2024-02-29 | [5 empty] | 1 | Coding | 3.5 | Disciussion Room function | Added discussion room management and model. | 0 | 0 | 0 | 0 | 0 | 3.5
2024-03-01 | 1 | [5 empty] | Review | 1 | Code Review | Reviewing peers code | 1 | 0 | 0 | 0 | 0 | 0
2024-03-01 |  |  | 1 |  |  |  | Coding and debugging | 3.5 | worked on implementing buy,cancel and renew membership with Haspmaps and displaying the memerbship details | Worked on completing the code and committed the final version | 0 | 0 | 3.5 | 0 | 0 | 0
2024-03-01 |  |  |  |  | 1 |  | Coding | 2 | Update Book details coding | Developing Functionality and Debugging | 0 | 0 | 0 | 0 | 2 | 0
2024-03-01 |  |  |  |  | 1 |  | Testing | 4 | Test cases Review | Reviewing peers code | 0 | 0 | 0 | 0 | 4 | 0
2024-03-01 |  | 1 |  |  |  |  | Debugging | 4 | working on Debugging for newsletter functionality with several testcases | Debuged test case | 0 | 4 | 0 | 0 | 0 | 0
2024-03-01 |  |  |  | 1 |  |  | Coding | 3 | Implementing Admin services, view news toString() | Functionality implementation of adminServices and to string on viewNews | 0 | 0 | 0 | 3 | 0 | 0
2024-03-01 |  |  |  |  | 1 |  | Testing | 2 | Developing initial test case for adding a book | Raw version of code developed for adding a book | 0 | 0 | 0 | 0 | 2 | 0
2024-03-02 |  |  | 1 |  |  |  | Code and Debug | 3 | Code review and debug changes for the membershipmanager class | Completed the code for the purpose mentioned besides | 0 | 0 | 3 | 0 | 0 | 0
2024-03-02 |  | 1 |  |  |  |  | code changes and Object diagrams | 3 | Creating object diagrams | Object diagrams | 0 | 3 | 0 | 0 | 0 | 0
2024-03-02 |  |  |  | 1 |  |  | Debugging | 2 | UI changes and Junit 4 to 5 conversions and rewriting testcases | rewrk on testcases | 0 | 0 | 0 | 2 | 0 | 0
2024-03-02 | [5 empty] | 1 | Coding | 3 | Presentation Room fuction | Refactored discussion roo code into presentation room code. | 0 | 0 | 0 | 0 | 0 | 3
2024-03-02 |  |  |  |  | 1 |  | Testing | 4 | Developing test case for Remove book and debugging add book test case | Debugged Add book test case and Implemented Remove book test case | 0 | 0 | 0 | 0 | 4 | 0
2024-03-02 | 1 | [5 empty] | Testing | 4 | Unit Test Cases | Unit Test cases for Search Implemented | 4 | 0 | 0 | 0 | 0 | 0
2024-03-03 | 1 | [5 empty] | Testing | 4 | Unit Test Cases | worked on some JUnit test cases for browse history | 4 | 0 | 0 | 0 | 0 | 0
2024-03-03 | [5 empty] | 1 | Coding and testing | 4.5 | Unit Test Cases | Refactored presentation room code and worked on unit test cases for user login and registration. | 0 | 0 | 0 | 0 | 0 | 4.5
2024-03-03 | 1 | [5 empty] | Testing | 3 | Unit Test Cases | Completed all the test cases | 3 | 0 | 0 | 0 | 0 | 0
2024-03-03 |  |  |  | 1 |  |  | Coding | 4 | Test cases for AdminServices, updatenews and viewnews edit on cases printing | Test cases written | 0 | 0 | 0 | 4 | 0 | 0
2024-03-03 | 1 | 1 | 1 | 1 | 1 | 1 | Group Discussion | 3 | Group Discussion | Final review of the code and finishing off the object diagrams | 3 | 3 | 3 | 3 | 3 | 3
2024-03-04 |  | 1 |  |  |  |  | report work | 1 | object diagram | submitted and committed object diagram for report work | 0 | 1 | 0 | 0 | 0 | 0
2024-03-04 | [5 empty] | 1 | Coding | 2 | Presentation room code. | Refactored Presentation room code. | 0 | 0 | 0 | 0 | 0 | 2
[10 empty] | Total hours | 32.5 | 32 | 32 | 34.5 | 34.5 | 33
[10 empty] | Total team hours | [6 empty] | 198.5
Milestone 3
2024-03-09 | 1 | 1 | 1 | 1 | 1 | 1 | Brainstorming session | 2 | Group Discussion | Discussion on the OCLs and biforcating task among team mates | 2 | 2 | 2 | 2 | 2 | 2
2024-03-06 |  |  |  | 1 |  |  | Coding | 3 | Coding | Implementation of OCLs | 0 | 0 | 0 | 3 | 0 | 0
2024-03-06 |  | 1 |  |  |  |  | OCL listing | 3 | brainstorming | Writing down all possible ocl constraints for the project | 0 | 3 | 0 | 0 | 0 | 0
2024-03-06 |  |  | 1 |  |  |  | OCL | 3.5 | OCL | Finding OCL's | 0 | 0 | 3.5 | 0 | 0 | 0
2024-03-06 | 1 | [5 empty] | Coding | 2 | Coding | Implementation of OCLs | 2 | 0 | 0 | 0 | 0 | 0
2024-03-07 | 1 | [5 empty] | Coding | 3.5 | Coding | Implementation of OCLs | 3.5 | 0 | 0 | 0 | 0 | 0
2024-03-07 |  |  |  | 1 |  |  | Coding | 3 | Coding | Implementation of OCLs | 0 | 0 | 0 | 3 | 0 | 0
2024-03-07 |  | 1 |  |  |  |  | OCL | 3 | OCL -Report | Converting the OCL statements to constraint. | 0 | 3 | 0 | 0 | 0 | 0
2024-03-07 |  |  | 1 |  |  |  | OCL-coding | 4 | Coding | Coding for the OCL assigned to me and writing their constraints | 0 | 0 | 4 | 0 | 0 | 0
2024-03-08 |  |  |  | 1 |  |  | Coding | 2.5 | Coding | Implementation of OCLs | 0 | 0 | 0 | 2.5 | 0 | 0
2024-03-08 |  |  |  |  | 1 |  | OCL Search | 3 | OCL brainstorming | Found OCLs | 0 | 0 | 0 | 0 | 3 | 0
2024-03-09 |  |  |  | 1 |  |  | Coding and Test | 4 | Coding | Implementation of OCLs | 0 | 0 | 0 | 4 | 0 | 0
2024-03-09 |  | 1 |  |  |  |  | Coding | 4 | Coding | Implementing the OCL's | 0 | 4 | 0 | 0 | 0 | 0
2024-03-09 |  |  | 1 |  |  |  | Coding | 3 | Code and debug | Worked on completing the ocl implementation and debug | 0 | 0 | 3 | 0 | 0 | 0
2024-03-10 | 1 | [5 empty] | Code Review | 2 | Code Reviews | Reviewed the code and merged | 2 | 0 | 0 | 0 | 0 | 0
2024-03-11 | 1 | [5 empty] | Coding | 3.5 | Coding | Implementation of OCLs | 3.5 | 0 | 0 | 0 | 0 | 0
2024-03-11 | [5 empty] | 1 | Coding | 3.5 | Coding and ocl | Written ocl constraints and updated code. | 0 | 0 | 0 | 0 | 0 | 3.5
2024-03-12 | [5 empty] | 1 | Coding | 3 | Coding | Written ocl constraints and updated code. | 0 | 0 | 0 | 0 | 0 | 3
2024-03-13 | [5 empty] | 1 | Coding | 4 | Presentation room code. | Ocl implementation for presentation room code. | 0 | 0 | 0 | 0 | 0 | 4
2024-03-13 |  | 1 |  |  |  |  | Debugging | 4 | Debugging the code | Debugging the code to complete the implementation | 0 | 4 | 0 | 0 | 0 | 0
2024-03-14 |  | 1 |  |  |  |  | Object diagram | 3 | Report Work | Adding object diagrams to the respective constraints | 0 | 3 | 0 | 0 | 0 | 0
2024-03-15 |  |  |  | 1 |  |  | Report work | 2 | Edit Report | Implementation of the OCL table | 0 | 0 | 0 | 2 | 0 | 0
2024-03-15 |  |  | 1 |  |  |  | Report work | 3 | Object diagram | Editing diagram in Report | 0 | 0 | 3 | 0 | 0 | 0
2024-03-15 | [5 empty] | 1 | Coding | 4 | Ocl for Presentation room | Ocl implementation for presentation room code. | 0 | 0 | 0 | 0 | 0 | 4
2024-03-16 | 1 | [5 empty] | Code Review | 2 | Code Reviews | Reviewed the code and merged | 2 | 0 | 0 | 0 | 0 | 0
2024-03-16 |  |  |  | 1 |  |  | Drawing object diagrams | 1.5 | Drawing object diagrams | Building diagrams in accordance to OCLs | 0 | 0 | 0 | 1.5 | 0 | 0
2024-03-16 | 1 | [5 empty] | Report work | 3 | Report Work | Started writing the report | 3 | 0 | 0 | 0 | 0 | 0
2024-03-16 |  |  |  |  | 1 |  | OCL coding | 5 | OCL implemented successfully | 90 percent of assigned OCL implemented | 0 | 0 | 0 | 0 | 5 | 0
2024-03-17 | 1 | 1 | 1 | 1 | 1 | 1 | report work | 2 | Discussion on report | Discussed on the report work | 2 | 2 | 2 | 2 | 2 | 2
2024-03-17 |  |  |  | 1 |  |  | Drawing object diagrams | 1.5 | Drawing object diagrams | Building diagrams in accordance to OCLs | 0 | 0 | 0 | 1.5 | 0 | 0
2024-03-17 |  |  |  |  | 1 |  | OCLcode review and OCL writing | 6 | Code refactor and OCL writing | Orgnized code for OCL and OCL in written form | 0 | 0 | 0 | 0 | 6 | 0
2024-03-18 |  |  |  |  | 1 |  | OCL diagrams | 2 | OCL diagrams | Editing diagram in Report | 0 | 0 | 0 | 0 | 2 | 0
2024-03-18 |  |  |  | 1 |  |  | report work | 2 | Edit Report | Formatting and segregating | 0 | 0 | 0 | 2 | 0 | 0
2024-03-18 | [5 empty] | 1 | report work | 2 | Ocl and diagrams | Added Ocls and diagram into the report | 0 | 0 | 0 | 0 | 0 | 2
2024-03-18 |  |  | 1 |  |  |  | report work | 3 | Report Work | Formatting and working on report | 0 | 0 | 3 | 0 | 0 | 0
2024-03-18 | 1 | 0 | 0 | 0 | 0 | 0 | report work | 2 | Completed the report | Fixed the format of the reports | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 22 | 21 | 20.5 | 23.5 | 20 | 20.5
[10 empty] | Total team hours | [6 empty] | 127.5
Milestone 4
2024-03-27 | 1 | 1 | 1 | 1 | 1 | 1 | Group Discussion | 2 | Group Discussion | Discussed on the diagrams and biforcated the work | 2 | 2 | 2 | 2 | 2 | 2
2024-03-27 |  |  |  | 1 |  |  | UML diagrams | 1.5 | Sequence Diagram | Paid user Fns | 0 | 0 | 0 | 1.5 | 0 | 0
2024-03-27 | 1 | [5 empty] | UML diagrams | 3 | Sequence Diagram | Sequence diagram for Presentation Room Booking | 3 | 0 | 0 | 0 | 0 | 0
2024-03-27 |  | 1 |  |  |  |  | UML diagrams | 3 | State Diagram | State diagram for asset | 0 | 3 | 0 | 0 | 0 | 0
2024-03-27 |  |  |  |  | 1 |  | UML diagrams | 3 | sequence diagram of renew and loan asset | sequence diagram of renew and loan asset | 0 | 0 | 0 | 0 | 3 | 0
2024-03-28 | [5 empty] | 1 | UML diagrams | 2.5 | State Diagram | Presentation Room | 0 | 0 | 0 | 0 | 0 | 2.5
2024-04-01 |  |  |  | 1 |  |  | UML diagrams | 1 | Sequence Diagram | Free user buys membership | 0 | 0 | 0 | 1 | 0 | 0
2024-04-02 | [5 empty] | 1 | UML diagrams | 1.5 | State Diagram | Modifications on presentation room diagram | 0 | 0 | 0 | 0 | 0 | 1.5
2024-04-02 |  |  |  |  | 1 |  | UML diagrams | 3 | communication diagrams | communication diagrams | 0 | 0 | 0 | 0 | 3 | 0
2024-04-02 |  |  | 1 |  |  |  | Class Diagram Updates | 2 | Updated the Class Diagram | Updated the Class Diagram | 0 | 0 | 2 | 0 | 0 | 0
2024-04-02 |  |  |  | 1 |  |  | UML diagrams | 2 | Sequence Diagram | Rework on Paid user Mng | 0 | 0 | 0 | 2 | 0 | 0
2024-04-02 | 1 | [5 empty] | UML diagrams | 3 | Communication Diagrams | Communication Diagrams | 3 | 0 | 0 | 0 | 0 | 0
2024-04-03 |  | 1 |  |  |  |  | Implementation | 4 | Coding | Code for return and fine asset | 0 | 4 | 0 | 0 | 0 | 0
2024-04-03 |  |  |  | 1 |  |  | UML diagrams | 2 | Communication diagrams | Comm diag for membership | 0 | 0 | 0 | 2 | 0 | 0
2024-04-04 | [5 empty] | 1 | UML diagrams | 2 | State Diagram | Added Ocl's to state diagram | 0 | 0 | 0 | 0 | 0 | 2
2024-04-05 | 1 | [5 empty] | UML diagrams | 3 | Communication Diagrams | Communication Diagrams | 3 | 0 | 0 | 0 | 0 | 0
2024-04-05 |  |  | 1 |  |  |  | UML diagrams | 4 | State Diagram | working on state diagrams for membership with ocls | 0 | 0 | 4 | 0 | 0 | 0
2024-04-05 | [5 empty] | 1 | UML diagrams | 2 | State Diagram | Modification of class diagram and Ocl's on state diagram | 0 | 0 | 0 | 0 | 0 | 2
2024-04-07 |  |  | 1 |  |  |  | Report Work | 4 | State Diagram and report | Worked on drafting the report and modification to the state diagram for the final version | 0 | 0 | 4 | 0 | 0 | 0
2024-04-07 | 1 | 1 | 1 | 1 | 1 | 1 | Group Discussion | 2 | Group Discussion | Reviewed the diagrams and started drafting the report | 2 | 2 | 2 | 2 | 2 | 2
2024-04-07 |  | 1 |  |  |  |  | UML diagrams | 3 | State Diagram | modifying state diagram and adding ocl | 0 | 3 | 0 | 0 | 0 | 0
2024-04-07 |  |  |  |  | 1 |  | UML diagrams | 2 | communication diagrams | communication diagrams | 0 | 0 | 0 | 0 | 2 | 0
2024-04-07 | [5 empty] | 1 | UML diagrams | 2 | State Diagram | Modification of Ocl's on state diagram | 0 | 0 | 0 | 0 | 0 | 2
2024-04-07 | 1 | [5 empty] | Report Work | 2 | Formating and Captioning | Format report | 2 | 0 | 0 | 0 | 0 | 0
2024-04-07 |  |  |  | 1 |  |  | Report Work | 0.5 | Formating and Captioning | Format report | 0 | 0 | 0 | 0.5 | 0 | 0
2024-04-07 |  |  |  | 1 |  |  | UML diagrams | 2.5 | Communication | Format reworking UML | 0 | 0 | 0 | 2.5 | 0 | 0
2024-04-07 |  |  |  |  | 1 |  | Report Work | 2 | Formatting and review | Format report | 0 | 0 | 0 | 0 | 2 | 0
2024-04-08 | [5 empty] | 1 | Report Work | 1 | Formating and editing | Worked on report | 0 | 0 | 0 | 0 | 0 | 1
[10 empty] | Total hours | 15 | 14 | 14 | 13.5 | 14 | 14
[10 empty] | Total Team hours | [6 empty] | 84.5
Milestone 5
2024-04-12 |  |  |  | 1 |  |  | Report Work | 2 | Roprt compilation of deliverables 1,2 & 3 | Reoriented deliverable 5 draft with compiling and formatting | 0 | 0 | 0 | 2 | 0 | 0
2024-04-13 | 1 | [5 empty] | Report Work | 3 | Fixed Class Diagram and worked on Object Diagrams | Fixed Class Diagram and worked on Object Diagrams | 3
2024-04-13 | [5 empty] | 1 | Report Work | 1 | Ocls and digrams | Added Ocls and diagrams into the report | 0 | 0 | 0 | 0 | 0 | 1
2024-04-13 |  |  |  |  | 1 |  | Object diagram | 1 | Ocl diagram changes | changed ocl diagram | 0 | 0 | 0 | 0 | 1 | 0
2024-04-13 |  |  | 1 |  |  |  | Report Work | 3 | Class diagram with OCL | Worked on ocl and class diagram | 0 | 0 | 3 | 0 | 0 | 0
2024-04-14 |  |  |  | 1 |  |  | Diagram rework | 2.5 | Ocl object diagram reworks | Worked on Object Diagram rework formatting |  |  |  | 2.5
2024-04-14 | [5 empty] | 1 | Report Work | 2.5 | Feedback changes and ocl diagrams | Updated ocl diagrams with properties and made feedback changes | 0 | 0 | 0 | 0 | 0 | 2.5
2024-04-14 |  |  |  |  | 1 |  | Report Work | 2 | Changes in ocl diagrams | Updated OCL diagrams and made feedback. | 0 | 0 | 0 | 0 | 2 | 0
2024-04-14 | 1 | 1 | 1 | 1 | 1 | 1 | Group Discussion | 1 | Discussion on pending items and report work | Discussion on pending items and report work | 1 | 1 | 1 | 1 | 1 | 1
[10 empty] | Total hours | 4 | 1 | 4 | 5.5 | 4 | 4.5 | 23
total team hours
[10 empty] | Total hour over project | 87.5 | 84.5 | 87 | 91 | 89 | 87
[10 empty] | Total team hours over project | [6 empty] | 526